# Assignment: Project Management Plan for Creative Work

## Objective

Create a basic project management plan for a creative project of your choice. This could be a design project, video production, marketing campaign, website build, or any other creative endeavor. Your plan should demonstrate how you would organize the project, communicate with stakeholders, and manage timelines and deliverables.

## Assignment Requirements

Your project management plan must include the following components:

### 1. Project Overview

- Project name

- Description (what is being created and why)

- Goals and objectives

- Key stakeholders (e.g., client, creative team, vendors)

### 2. Timeline & Milestones

- Project start and end dates

- Key phases (e.g., planning, design, production, review, launch)

- Milestones with dates (e.g., concept approval, first draft, final delivery)

### 3. Deliverables

- Clear list of all deliverables for the project

  - What is being delivered (e.g., logo, video file, website, poster)

  - Due dates for each deliverable

  - Responsible team members (optional but encouraged)

### 4. Stakeholder Communication Plan

- Methods of communication (e.g., email, meetings, video calls, project management software)

- Frequency of communication (e.g., weekly check-ins, milestone reviews)

- Feedback loops: How will feedback be collected, reviewed, and incorporated?

- Escalation process: What happens if there is a major issue?

### 5. Risk Management

- Identify at least 2 potential risks (e.g., missed deadlines, unclear feedback)

- How you would mitigate them

Include an executive summary and a closing for your project document.

## Competency-Based Rubric: Project Management Plan for Creative Work

| Competency | Exemplary (4) | Proficient (3) | Developing (2) | Beginning (1) |
| --- | --- | --- | --- | --- |
| 1. Project Definition & Clarity (Overview, goals, stakeholders) | Project overview is clear, concise, and compelling. Goals are measurable and well-aligned with the project’s purpose. Stakeholders are accurately identified with relevant roles. | Overview is mostly clear; goals are stated but may be less measurable. Stakeholders are identified with minor omissions. | Overview is vague or lacks clear connection to goals. Some stakeholders missing or not clearly defined. | Overview is unclear or incomplete. Goals are missing or irrelevant. Stakeholders are not identified. |
| 2. Timeline & Milestone Planning | Timeline covers all key phases with logical sequencing. Milestones are specific, dated, and achievable. Shows strong awareness of dependencies. | Timeline includes most key phases and milestones; sequencing is mostly logical. Some dates or dependencies unclear. | Timeline is incomplete or missing important phases. Milestones lack clarity or realistic dates. | Timeline is missing or minimal. No clear milestones provided. |
| 3. Deliverables Definition | All deliverables are clearly listed with detailed descriptions, due dates, and responsible parties. Deliverables align with project goals. | Most deliverables are listed with due dates and some responsible parties. Minor gaps in clarity or alignment. | Deliverables are listed but lack descriptions, due dates, or responsible assignments. Some misalignment with goals. | Deliverables are unclear, incomplete, or missing key items. |
| 4. Stakeholder Communication Plan | Communication methods, frequency, and feedback loops are clearly defined and realistic. Escalation process is clear and actionable. | Communication plan includes most required elements; escalation process may lack detail. | Communication plan is minimal; feedback process or escalation steps are vague. | No clear communication plan or missing multiple required elements. |
| 5. Risk Identification & Mitigation | At least two relevant risks are clearly identified with realistic, actionable mitigation strategies. Shows strong anticipation of challenges. | Risks are identified with general mitigation strategies. Some lack depth or realism. | Risks are mentioned but with unclear or impractical mitigation strategies. | Risks are missing or mitigation strategies are absent. |
| 6. Organization & Professionalism (Executive Summary, Closing, Formatting) | Document is well-structured with a strong executive summary and closing. Professional formatting, free of errors, and easy to navigate. | Document includes required sections with minor issues in clarity or formatting. | Document is missing some required sections or contains multiple formatting/clarity issues. | Document is poorly organized, missing sections, or difficult to read. |
| 7. Application of Project Management Principles | Plan demonstrates deep understanding of project management concepts and adapts them effectively to a creative context. | Plan applies project management concepts appropriately with minor gaps. | Plan shows limited application of project management principles; may misapply some concepts. | Plan does not reflect understanding or use of project management principles. |